## Slide 1: CMS Contract On-Boarding for CCSQ Overview
August 2024

## Slide 2: Introduction To Contractor On-Boarding
Welcome to the Contractor On-Boarding Overview. This presentation is designed to provide you with a comprehensive understanding of the contractor on-boarding process, outlining what is expected from you as Contractor Representatives (COR)
We will cover the key steps involved in on-boarding new contractors, including the necessary documentation, timeline, and communication protocols
Our goal is to ensure a seamless and efficient on-boarding experience that aligns with our organizational standards and compliance requirements
By the end of this briefing, you will have a clear understanding of your roles and responsibilities in facilitating the successful integration of new contractors into our team

## Slide 3: What is On-Boarding?
Contractor on-boarding is the comprehensive process required when a new CMS contract is awarded, ensuring that the contractor can effectively utilize QualityNet tools and services
This process involves the COR collaborating with the new contractors to complete the intake form for the Contract Engagement Team (CET). The CET then executes all the necessary tasks to set up the contractor's access, ensuring a seamless integration into the organization's systems and workflows
NOTE: The COR must have EUA/HARP ID and Atlassian access for access to the form
There is an On-boarding Word template that can be used to compile information needed for on-boarding form

## Slide 4: Timeline for On-Boarding / Off-Boarding
1. Initial Notification and Preparation (60 Days Prior to Award)
2. Contract Award and Intake Form Completion
3. On-Boarding Preparation and Planning
4. Regular Communication and Support
5. Post On-Boarding Review
6. Contract Closeout (60 Days Prior to Period of Performance Ending)

## Slide 5: 60 Days Prior to Award
The Initial Notification and Preparation (60 Days Prior to Award)
The Contracting Officer's Representative (COR) notifies the Contract Engagement Team (CET) of a new contract solicitation and provides an estimated award date by emailing to: ISGContractorOnboardingServices@cms.hhs.gov
The COR and CET identify high-level service requirements and gather all necessary information for the on-boarding process

## Slide 6: On-Boarding Continued
There is an On-boarding Word template that can be used to compile information needed for onboarding
The COR and contract POCs discuss the types of system access available to the contractor and agree upon what is appropriate given the duties to be performed under the contract
To see the list of tools and services in this brief, or visit the QualityNet Communications Hub

## Slide 7: Preparation and Planning
On-Boarding Preparation and Planning
The CET reviews the intake form and prepares for the on-boarding process. This includes setting up initial meetings and planning the necessary steps for system access and configuration

## Slide 8: Execution
On-Boarding Execution (Within 5-10 Business Days)
Conduct the ISG Contract Onboarding Services meeting to discuss on-boarding requirements and timelines
The CET executes all tasks to set up contractor access to QualityNet tools, services, and the CCSQ Data Repository (CDR). This includes configuring accounts, account permissions, and providing necessary training materials

## Slide 9: Communication and Support
Regular Communication and Support
Hold contract calls and regular communication to ensure the on-boarding process is progressing smoothly and address any issues or questions that arise
Post On-Boarding Review
Upon completion of the on-boarding process, conduct a post-engagement survey to gather feedback and ensure all requirements are met

## Slide 10: What’s Next
August 2024

## Slide 11: What is Next
Conduct contract on-boarding services meeting
  The CET conducts a meeting with the CMS COR and new contractor to confirm eligibility for the services identified in the Onboarding Intake Form and sends a request for approval of these services to the CMS service leads for processing
Complete contract on-boarding
  After the CMS Service Leads have processed the request, the ISG Contract Onboarding Services team prepares and sends a welcome package to the New Contractor’s Security Official (SO) to complete the engagement process. The welcome package includes the following information:
    List of SO Responsibilities
    List of Approved Services
    Description of Approved Services
    Instructions for Onboarding Users
  Upon receipt of this welcome package and informational materials, the New Contractor SO can begin the process of onboarding new users into the QualityNet IT Services. Access is based on the list of approved services provided in the package

## Slide 12: QualityNet Services
The following slides are QualityNet Services.
The COR works with the CET to identify high-level service requirements for the new contract to gain a better understanding of what QualityNet IT Services will be applicable:
- Atlassian is a cloud-based collaboration and planning service. Includes Jira and Confluence
- Unified File Management automates and secures data exchange to meet the needs for reporting and sharing data between both internal and external resources

## Slide 13: QualityNet Services Continued
Centralized Data Repository (CDR) and CCSQ Analytics Platform
The CDR consists of single, well-defined, and high-quality versions of all the data entities within the CCSQ organizational ecosystem.
The CCSQ Analytics Platform provides high-performance, in-memory analytics in an open, cloud-enabled, run-time environment. Currently, it consists to two analytic tools – Databricks.
- CCSQ QuickSight is a BI Tool allowing users to create or access interactive dashboards and reports
- ServiceNow is the ticketing platform that the CCSQ Service Center and QualityNet community use for logging Incidents or Service Requests and working different request types
- Slack is a collaboration tool enabling users to connect with individuals and groups within the QualityNet community

## Slide 14: QualityNet Communication Services
QualityNet Mailer is a list management system that is used to assist ADOs and contractors in communicating with large groups of end-users, program participants, and stakeholders. Contracts have the option to create their own lists and to sign up to receive existing listservs
QualityNet Communications Hub is a public space for news, guidance, and information on QualityNet IT Services. It contains information such as announcements, upcoming training events, and more
SurveyMonkey is an online survey software tool that helps you to create and run professional online surveys

## Slide 15: QualityNet Development Tools
Ansible Tower is an agentless Open-Source automation engine that can be used to automate software provisioning, configuration management, application deployment and other IT activities
QualityNet-Github Enterprise Cloud is the Open-Source solution used by QualityNet to implement Software configuration management (SCM)
QualityNet Cloud is an AWS based public cloud solution that enables the QualityNet program to utilize AWS cloud services in a manner that meets CMS security, architecture, and governance requirements
Jenkins is an Open-Source automation and orchestration engine Jenkins offers a simple way to help automate the non-human parts of the software development process

## Slide 16: More Development Tools
New Relic is a Software as a Service (SaaS) offering to monitor resources such as infrastructure, applications, and Amazon Web Service (AWS) endpoints for applications in the QualityNet cloud
Nexus RM is the repository management solution that is used by QualityNet to store and manage whatever libraries and other binary artifacts that the users require
Splunk is a powerful tool for searching and exploring data. It can help predict, identify, and solve problems related to business, information technology (IT), DevOps, and security in real-time
Zscaler is an alternative to VPN that uses a different method of allowing users to access resources within the QualityNet network

## Slide 17: Contract Off-Boarding
Contract Closeout (60 Days Prior to Period of Performance Ending)
The COR notifies the CET of the upcoming end of the contract period by emailing to: ISGContractorOnboardingServices@cms.hhs.gov
The CET ensures that all access and services are appropriately terminated and conducts any necessary closeout procedures

## Slide 18: Questions